## Activities
Activity ID | Activity Name | Activity Status | WBS Code | Original Duration | Start Date | Finish Date | Budgeted Cost
A1000 | Notice to Proceed | Completed | PROJ.1 | 0 | 2026-01-05 | 2026-01-05 | 0
A1010 | Site Mobilization | In Progress | PROJ.1.1 | 10 | 2026-01-06 | 2026-01-19 | 15000
A1020 | Excavation & Earthwork | Not Started | PROJ.1.1 | 15 | 2026-01-20 | 2026-02-09 | 45000
A1030 | Foundation Pouring | Not Started | PROJ.1.2 | 20 | 2026-02-10 | 2026-03-04 | 85000
A1040 | Structural Steel Erection | Not Started | PROJ.1.2 | 30 | 2026-03-05 | 2026-04-15 | 120000

## WBS
WBS Code | WBS Name
PROJ.1 | Project Construction
PROJ.1.1 | Site Preparation
PROJ.1.2 | Substructure & Structure